## Sheet1
Table1. Definitions, Acronyms, and Abbreviations
Name |  | Definition
x |  | Selected Person
VH |  | Very High Priority
H |  | High Priority
M |  | Medium Priority
A |  | Approved
Y |  | Yes
N |  | No
| Scrum Meeting Minutes |  | Target Personas |  |  |  | Status |  | Approval
|  |  | LongNHK | TanND | BinhLP | YNX | Degree of priority | Task completion | LongNHK | Mr. QuanDDM
Date: 12/05/2015
Raspberry PI 2
| Development environment for Raspberry |  | x | x | x | x | H | Y | A | A
Report 1
| Orienting the way writing report 1 |  | x | x | x | x | VH | Y | A | A
Date: 16/05/2015
Hand Detection
| Extracting background color |  | x |  |  |  | VH | Y | A | A
| Capturing images from camera and showing them to user |  |  | x |  |  | VH | Y | A | A
Portable System
| Choosing type of battery |  |  |  |  | x | H | Y | A | A
| Choosing voltage regulator circuit |  |  |  | x |  | H | Y | A | A
Report 1
| Reviewing report 1 |  | x | x | x | x | H | Y | A | A
Date: 19/05/2015
Hand Detection
| Demo extracting background color |  | x |  |  |  | H | Y | A | A
| Demo capturing images from camera and showing them to user |  |  | x |  |  | H | Y | A | A
Portable System
| Reviewing battery |  | x | x | x | x | M | Y | A | A
| Reviewing voltage regulator circuit |  | x | x | x | x | M | Y | A | A
Report 2
| Orienting the way writing report 2 |  | x | x | x | x | VH | Y | A | A
Date: 23/05/2015
Hand Detection
| Extracting hand color |  | x |  |  |  | VH | Y | A | A
| Finding the hand contours on the hand binary image |  |  | x |  |  | VH | Y | A | A
Portable System
| Connecting components |  |  |  | x | x | H | Y | A | A
Report 2
| Reviewing report 2 |  | x | x | x | x | H | Y | A | A
Date: 26/05/2015
Hand Detection
| Extracting hand color |  | x |  |  |  | H | Y | A | A
| Designing QT Linux GUI which of subtracting color |  |  | x |  |  | H | Y | A | A
Portable System
| Demo fully made portable system |  |  |  | x | x | H | Y | A | A
Report 3
| Orienting the way writing report 3 |  | X | x | x | x | VH | Y | A | A
Date: 30/05/2015
Hand Detection
| Subtracting color to get hand binary image |  | x |  |  |  | VH | Y | A | A
| Finding the hand contours on the hand binary image |  |  | x |  |  | VH | Y | A | A
Portable System
| Demo adjusted portable system |  |  |  | x | x | M | Y | A | A
Report 3
| Orienting the way writing report 3 |  | x | x | x | x | VH | Y | A | A
Date: 02/06/2015
Hand Detection
| Training SVM |  | x |  |  |  | VH | Y | A | A
| Creating SQLite database |  |  | x |  |  | VH | Y | A | A
| Designing QT Linux GUI which of steps recognition |  |  |  | x | x | M | Y | A | A
Report 3
| Reviewing report 3 |  | x | x | x | x | VH | Y | A | A
Date: 06/06/2015
Hand Detection
| Defining features to recognize |  | x |  |  |  | VH | Y | A | A
| Defining the meaning word of the SVM result from database |  |  | x |  |  | VH | Y | A | A
Portable System
| Designing QT Linux GUI which of the recognition flow |  |  |  | x | x | M | Y | A | A
Report 3
| Reviewing report 3 |  | x | x | x | x | VH | Y | A | A
Date: 09/06/2015
Hand Detection
| Defining features to recognize |  | x |  |  |  | VH | Y | A | A
| Defining the meaning word of the SVM result from database |  |  |  |  | x | M | Y | A | A
Result via sound
| Choosing text to speech opensource |  |  | x | x |  | H | Y | A | A
Report 4
| Orienting the way writing report 4 |  | x | x | x | x | VH | Y | A | A
Date: 13/06/2015
Hand Detection
| Features extraction |  | x |  |  |  | VH | Y | A | A
Result via sound
| Changing pronunciation of word |  |  | x |  | x | H | Y | A | A
| Implementing text to speech opensource |  |  | x | x |  | M | Y | A | A
Report 4
| Orienting the way writing report 4 |  | x | x | x | x | VH | Y | A | A
Date: 16/06/2015
Hand Detection
| Recognizing the hand sign by SVM |  | x |  |  |  | VH | Y | A | A
Result via sound
| Changing pronunciation of word |  |  | x |  | x | H | Y | A | A
| Showing the recognition result via sound |  |  |  | x |  | M | Y | A | A
Report 4
| Reviewing report 4 |  | x | x | x | x | VH | Y | A | A
Date: 20/06/2015
Hand Detection
| Showing the recognition result via text |  | x |  |  |  | H | Y | A | A
Result via sound
| Changing pronunciation of word |  |  |  |  | x | H | Y | A | A
| Showing the recognition result via sound |  |  |  | x |  | M | Y | A | A
Report 4
| Reviewing report 4 |  | x | x | x | x | H | Y | A | A
Date: 30/06/2015
Controlling function
| Defining operations of function |  | x | x |  |  | VH | Y | A | A
Monitor the battery capacity
| Choosing chip voltage comparator |  |  |  | x | x | H | Y | A | A
Report 5
| Orienting the way writing report 5 |  | x | x | x | x | VH | Y | A | A
Date: 04/07/2015
Controlling function
| Implementing operations of function |  | x | x |  |  | VH | Y | A | A
Monitor the battery capacity
| Choosing zener |  |  |  | x | x | H | Y | A | A
Report 5
| Orienting the way writing report 5 |  | x | x | x | x | VH | Y | A | A
Date: 07/07/2015
Controlling function
| Demo implementing operations of function |  | x | x |  |  | H | Y | A | A
Monitor the battery capacity
| Reviewing the chip voltage comparator and zener |  | x | x | x | x | VH | Y | A | A
Report 5
| Orienting the way writing report 5 |  | x | x | x | x | VH | Y | A | A
Date: 11/07/2015
Controlling function
| Designing QT Linux GUI which of the flow of operations |  | x | x |  |  | H | Y | A | A
Monitor the battery capacity
| Constructing circuit |  |  |  | x | x | VH | Y | A | A
Report 5
| Reviewing report 5 |  | x | x | x | x | VH | Y | A | A
Date: 14/07/2015
Controlling function
| Synchronizing between hand gestures and operations of function |  | x | x |  |  | VH | Y | A | A
Monitor the battery capacity
| Adjusting the device components |  |  |  | x | x | H | Y | A | A
Report 5
| Reviewing report 5 |  | x | x | x | x | VH | Y | A | A
Date: 18/07/2015
Controlling function
| Demo synchronizing between hand gestures and operations of function |  | x | x |  |  | M | Y | A | A
Portable System
| Connecting to the system |  |  |  | x | x | VH | Y | A | A
Report 5
| Reviewing report 5 |  | x | x | x | x | VH | Y | A | A
Date: 21/07/2015
Hand Detection
| Defining more features to recognize |  | x | x | x | x | VH | Y | A | A
Report 5
| Reviewing report 5 |  | x | x | x | x | H | Y | A | A
Date: 25/07/2015
Hand Detection
| Extracting features |  | x |  |  |  | VH | Y | A | A
| Improving camera setting |  |  | x |  | x | M | Y | A | A
Stable Environment
| Providing two LEDs to balance light |  |  |  | x | x | H | Y | A | A
Report 5
| Reviewing report 5 |  | x | x | x | x | H | Y | A | A
Date: 28/07/2015
Hand Detection
| Demo extracting features |  | x |  |  |  | H | Y | A | A
| Improving background - hand color subtraction |  | x | x |  |  | VH | Y | A | A
| Demo improving camera setting |  |  | x |  | x | M | Y | A | A
Stable Environment
| Demo balancing light |  |  |  | x | x | M | Y | A | A
Report 6
| Orienting the way writing report 6 |  | x | x | x | x | VH | Y | A | A
Date: 01/08/2015
Hand Detection
| Improving background - hand color subtraction |  | x | x |  |  | H | Y | A | A
Learning Function
| Creating database |  |  | x |  |  | H | Y | A | A
| Designing GUI |  |  | x |  | x | M | Y | A | A
| Implementing the practice function of learning |  | x |  | x |  | M | Y | A | A
Report 6
| Orienting the way writing report 6 |  | x | x | x | x | VH | Y | A | A
Date: 04/08/2015
Hand Detection
| Training SVM |  | x |  |  |  | VH | Y | A | A
Learning Function
| Managing database |  |  | x |  |  | M | Y | A | A
| Designing GUI |  |  | x |  | x | H | Y | A | A
ON/OFF the system
| Choosing switch button |  |  |  | x |  | H | Y | A | A
Report 6
| Orienting the way writing report 6 |  | x | x | x | x | VH | Y | A | A
Date: 08/08/2015
Learning Function
| Implementing the practice function of learning |  | x |  | x |  | VH | Y | A | A
| Demo GUI |  |  | x |  | x | H | Y | A | A
ON/OFF the system
| Constructing circuit |  |  |  | x | x | VH | Y | A | A
Report 6
| Reviewing report 6 |  | x | x | x | x | VH | Y | A | A
Date: 11/08/2015
Learning Function
| Demo learning function |  | x |  | x |  | H | Y | A | A
| Demo GUI |  |  | x |  | x | M | Y | A | A
ON/OFF the system
| Demo constructed circuit |  |  |  | x | x | H | Y | A | A
| Connecting to the system |  |  |  | x | x | VH | Y | A | A
Report 6
| Reviewing report 6 |  | x | x | x | x | VH | Y | A | A