## Product Backlog
ID | Theme | User Type | Wants to... | So that... | So that... | Priority | Sprint
1 | Detection | User | keep track their hand gesture |  | can see his/her hand in the screen | Very High | 1
2 | Device | User | the system is a portable system |  | move the device easily and use it more flexibly | High | 1
3 | Recognition | User | recognize the hand signs |  | express the same meaning to the partner can understand | Very High | 2
4 | Recognition | User | receive the recognition result via text and sound |  | express the translated content in a clearly way | High | 2
5 | Detection | User | control the system functions by hand gesture |  | perform and move beetween the system functions | High | 3
6 | Power | User | know remaining of battery capacity |  | can monitor the use of device | High | 3
7 | Recognition | User | increase the accuracy of the recognition result |  | raise the reliability of the translated content | Very High | 4
8 | Learning | User | learn the hand sign language |  | learn new signs or pratice his/her signs | Medium | 4
9 | Device | User | turn on/off the system |  | can turn on/off the device according to the demand | Medium | 4

## Sprint Backlog
Sprint | User Story | Time (est) | Time (spent) | Time (left) | Task | Time (est) | Who's working | Status | Work Done per week per task [Days]
| Project Name: "Vietnamese Language Sign Recognition" Started: 12-05-2015 | [7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
|  | 0 | 0 | 0 | bar: Work Done per week per task [Days] 6 to Work Done per week per task [Days] 7
1 | As a user, I want to keep track my hand gesture | 15 | 15 | 0 | Setup development environment for Raspberry PI and laptops | 3 | All Team | Done | Work Done per week per task [Days] 1: 3
[5 empty] | Capturing images from camera and showing them to user | 4 | TanND | Done | Work Done per week per task [Days] 1: 1; Work Done per week per task [Days] 2: 3
[5 empty] | Extracting background color | 4 | LongNHK | Done | Work Done per week per task [Days] 1: 1; Work Done per week per task [Days] 2: 3
[5 empty] | Extracting hand color | 4 | LongNHK | Done | Work Done per week per task [Days] 2: 2; Work Done per week per task [Days] 3: 2
[5 empty] | Subtracting color to get hand binary image | 4 | LongNHK | Done | bar: Work Done per week per task [Days] 4
[5 empty] | Finding the hand contours on the hand binary image | 4 | TanND | Done | Work Done per week per task [Days] 2: 2; Work Done per week per task [Days] 3: 2
[5 empty] | Designing QT Linux GUI | 4 | TanND | Done | Work Done per week per task [Days] 3: 3; Work Done per week per task [Days] 4: 1
| As a user, I want the system is a portable system | 15 | 15 | 0 | Choose type of battery | 3 | YNX | Done | Work Done per week per task [Days] 1: 1; Work Done per week per task [Days] 2: 2
[5 empty] | Choose voltage regulator circuit | 3 | BinhLP | Done | Work Done per week per task [Days] 1: 1; Work Done per week per task [Days] 2: 2
[5 empty] | Connecting components | 5 | BinhLP + YNX | Done | Work Done per week per task [Days] 2: 3; Work Done per week per task [Days] 3: 2
[5 empty] | Adjusting the device components | 4 | BinhLP + YNX | Done | Work Done per week per task [Days] 3: 3; Work Done per week per task [Days] 4: 1
2 | As a user, I want to recognize the hand signs | 13 | 13 | 0 | Creating SQLite database | 2 | TanND | Done | Work Done per week per task [Days] 4: 2
[5 empty] | Training SVM | 3 | LongNHK | Done | Work Done per week per task [Days] 4: 3
[5 empty] | Defining features to recognize | 3 | LongNHK | Done | Work Done per week per task [Days] 4: 1; Work Done per week per task [Days] 5: 2
[5 empty] | Features extraction | 4 | LongNHK | Done | Work Done per week per task [Days] 5: 3; Work Done per week per task [Days] 6: 1
[5 empty] | Recognizing the hand sign by SVM | 3 | LongNHK | Done | Work Done per week per task [Days] 6: 3
[5 empty] | Defining the meaning word of the SVM result from database | 3 | TanND + YNX | Done | Work Done per week per task [Days] 4: 2; Work Done per week per task [Days] 5: 1
[5 empty] | Designing QT Linux GUI | 4 | BinhLP + YNX | Done | Work Done per week per task [Days] 4: 4
| As a user, I want to receive the recognition result via text and sound | 10 | 10 | 0 | Choosing text to speech opensource | 3 | TanND + BinhLP | Done | Work Done per week per task [Days] 5: 3
[5 empty] | Implementing text to speech opensource | 3 | TanND + BinhLP | Done | Work Done per week per task [Days] 5: 1; Work Done per week per task [Days] 6: 2
[5 empty] | Changing pronunciation of word | 4 | TanND + YNX | Done | Work Done per week per task [Days] 6: 3; Work Done per week per task [Days] 7: 1
[5 empty] | Showing the recognition result via text | 2 | LongNHK | Done | bar: Work Done per week per task [Days] 6 to Work Done per week per task [Days] 7
[5 empty] | Showing the recognition result via sound | 4 | BinhLP + YNX | Done | Work Done per week per task [Days] 6: 3; Work Done per week per task [Days] 7: 1
3 | As a user, I want to control the system functions by hand gesture | 15 | 15 | 0 | Defining operations of function | 3 | LongNHK + TanND | Done | Work Done per week per task [Days] 7: 3
[5 empty] | Implementing operations of function | 3 | LongNHK + TanND | Done | Work Done per week per task [Days] 7: 1; Work Done per week per task [Days] 8: 2
[5 empty] | Designing QT Linux GUI | 4 | LongNHK + TanND | Done | Work Done per week per task [Days] 8: 3; Work Done per week per task [Days] 9: 1
[5 empty] | Synchronize between hand gestures and operations of function | 5 | LongNHK + TanND | Done | Work Done per week per task [Days] 9: 4; Work Done per week per task [Days] 10: 1
| As a user, I want to know remaining of battery capacity | 15 | 15 | 0 | Choosing chip voltage comparator | 3 | BinhLP + YNX | Done | Work Done per week per task [Days] 7: 3
[5 empty] | Choosing zener | 3 | BinhLP + YNX | Done | Work Done per week per task [Days] 7: 1; Work Done per week per task [Days] 8: 2
[5 empty] | Constructing circuit | 4 | BinhLP + YNX | Done | Work Done per week per task [Days] 8: 3; Work Done per week per task [Days] 9: 1
[5 empty] | Adjusting the device components | 2 | BinhLP + YNX | Done | Work Done per week per task [Days] 9: 2
[5 empty] | Connecting to the system | 3 | BinhLP + YNX | Done | Work Done per week per task [Days] 9: 2; Work Done per week per task [Days] 10: 1
4 | As a user, I want to increase the accuracy of the recognition result | 11 | 11 | 0 | Defining more features to recognize | 3 | All Team | Done | Work Done per week per task [Days] 10: 3
[5 empty] | Extracting features | 3 | LongNHK | Done | Work Done per week per task [Days] 10: 1; Work Done per week per task [Days] 11: 2
[5 empty] | Providing two LEDs to balance light | 3 | BinhLP + YNX | Done | Work Done per week per task [Days] 10: 1; Work Done per week per task [Days] 11: 2
[5 empty] | Improving camera setting | 2 | TanND + YNX | Done | bar: Work Done per week per task [Days] 10 to Work Done per week per task [Days] 11
[5 empty] | Improving background - hand color subtraction | 2 | LongNHK + TanND | Done | Work Done per week per task [Days] 11: 3
[5 empty] | Training SVM | 3 | LongNHK | Done | Work Done per week per task [Days] 12: 2
| As a user, I want to learn hand sign language | 8 | 8 | 0 | Creating database | 2 | TanND | Done | bar: Work Done per week per task [Days] 11
[5 empty] | Managing database | 2 | TanND | Done | Work Done per week per task [Days] 12: 2
[5 empty] | Implementing the practice function of learning | 4 | LongNHK + BinhLP | Done | Work Done per week per task [Days] 12: 4
[5 empty] | Designing GUI | 4 | TanND + YNX | Done | Work Done per week per task [Days] 12: 4
| As a user, I want to turn on/off the system | 8 | 8 | 0 | Choosing switch button | 2 | BinhLP | Done | Work Done per week per task [Days] 11: 2
[5 empty] | Constructing circuit | 3 | BinhLP + YNX | Done | Work Done per week per task [Days] 12: 3
[5 empty] | Connecting to the system | 3 | BinhLP | Done | Work Done per week per task [Days] 12: 3
| TOTAL | 60 | 60 | 0 |  |  |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| Daily burnout | 0 | [6 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| Total time left (from estimate) | [5 empty] | Estimate | 60 | 55 | 50 | 45 | 40 | 35 | 30 | 25 | 20 | 15 | 10 | 5 | 0
| Total time left (from spent) | [5 empty] | Burnout | 60 | 55 | 50 | 45 | 40 | 35 | 30 | 25 | 20 | 15 | 10 | 5 | 0
| Complexity (story points) | 31

## User types
User
Moderator
Client administrator
Developer

## Team members
Working hours per day
LongNHK | 3
TanND | 3
BinhLP | 3
YNX | 3
All Team
BinhLP + YNX
LongNHK + TanND
LongNHK + BinhLP
LongNHK + YNX
TanND + BinhLP
TanND + YNX

## Task statuses
TODO
Working
Done
Blocked
Verify