## Sheet1
Table1. Definitions, Acronyms, and Abbreviations
Name |  | Definition
X |  | Selected Person
VH |  | Very High Priority
H |  | High Priority
M |  | Medium Priority
A |  | Approved
Y |  | Yes
N |  | No
| Scrum Meeting Minutes |  | Target Personas |  |  |  | Status |  | Approval
|  |  | LongNHK | TanND | BinhLP | YNX | Degree of priority | Task completion | LongNHK | Mr. QuanDDM
Date: 12/05/2015
Raspberry PI 2
| Development environment for Raspberry |  | X | X | X | X | VH | Y | A | A
Report 1
| Orienting the way writing report 1 |  | X | X | X | X | H | Y | A | A
Date: 16/05/2015
Hand Detection
| Extracting background color |  | X |  |  |  | H | Y | A | A
| Capturing images from camera and showing them to user |  |  | x |  |  | H | Y | A | A
Portable System
| Choosing type of battery |  |  |  |  | x | M | Y | A | A
| Choose voltage regulator circuit |  |  |  | x |  | M | Y | A | A
Report 1
| Reviewing report 1 |  | X | X | X | X | VH | Y | A | A