## Sprint Backlog weeks 3-4
User Story | Time (est) | Time (spent) | Time (left) | Task | Time (est) | Who's working | Status | Work Done per day per task [Hours]
GOAL: "Recommendation Engine prototype and Simple Authentication" Started: 20-01-2014 | [7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
| 0 | 0 | 0
Get recommended activities | 23 | 23 | 4 | activity wizard UI | 4 | Cassio | Done | Work Done per day per task [Hours] 1: 4
|  |  |  | Separate scripts load only for the needed pages | 5 | Cassio | Done | Work Done per day per task [Hours] 2: 2; Work Done per day per task [Hours] 3: 3
|  |  |  | Add results from the current recommendation page in the results (i.e. most popular products from brans/shops the user follows) | 4 | Cassio | Done | Work Done per day per task [Hours] 5: 4
|  |  |  | Most popular products page | 3 | Cassio | Done | Work Done per day per task [Hours] 4: 2; Work Done per day per task [Hours] 5: 1
|  |  |  | Track activity views | 5 | Cassio | Working | Work Done per day per task [Hours] 8: 3
|  |  |  | Pagination | 2 | Cassio | TODO
Comment moderation interface | 9 | 9 | 5 | Client side validation | 2 | Ana | Done | Work Done per day per task [Hours] 4: 2
|  |  |  | Design UI | 4 | Ana | Working | Work Done per day per task [Hours] 5: 2
|  |  |  | Flag a comment | 3 | Ana | TODO
Authentication | 21 | 21 | 14 | Define role based authentication | 5 | John | Working | Work Done per day per task [Hours] 3: 2
|  |  |  | Tag brand categories | 6 | John | TODO
|  |  |  | Implement Candidate Filter Strategy | 7 | David | Working | Work Done per day per task [Hours] 3: 1; Work Done per day per task [Hours] 4: 2; Work Done per day per task [Hours] 5: 2
|  |  |  | decouple fetch products/users from the fetch preferences | 3 | Cassio | TODO
TOTAL | 53 | 53 | 23 |  |  |  |  | 4 | 2 | 6 | 6 | 9 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0
Daily burnout | -67 | [6 empty] | 12 | 12 | 12 | 12 | 12 | 0 | 0 | 12 | 12 | 12 | 12 | 12 | 0 | 0
Total time left (from estimate) | [5 empty] | Estimate | 53 | 41 | 29 | 17 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total time left (from spent) | [5 empty] | Burnout | 53 | 49 | 47 | 41 | 35 | 26 | 26 | 26 | 23 | 23 | 23 | 23 | 23 | 23 | 23
Complexity (story points) | 31

## Product Backlog
Priority | Story Points | Sprint | User Type | Wants to... | So that... | So that...
1 | 8 | 1 | User | Get recommended activities |  | He/she can discover new interesting activities
2 | 5 | 1 | Moderator | Comment moderation interface |  | He will be able to remove comments and mark as spam
3 | 5 | 1 | Client administrator | Authentication |  | He can sign in on the system and manage his content
4 |  | 2 | User | Notifications for friend's activities |  | Users will be aware of their friends' activities
5 |  | 2 | User | Search Activity |  | Users wil be able to find activities that matches with some criteria
6
7
8
9
10
11
12
13
14
15
Past stories
| 5 | 1 | Developer | Get all tools working on local machine
| 5 | 1 | Configuration Manager | List infrastructure to deploy the application | the code can run

## User types
User
Moderator
Client administrator
Advertiser
Developer
Configuration Manager

## Team members
Working hours per day
Cassio | 3
John | 3
David | 3
Ana | 3

## Task statuses
TODO
Working
Done
Blocked
Verify