## Sprint 1 Backlog
User Story | Time (est) | Time (spent) | Time (left) | Task | Time (est) | Who's working | Status | Work Done per day per task [Hours]
[8 empty] | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3
Project Name: "Vietnamese Language Sign Recognition" Started: 12-05-2015 | [7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| 0 | 0 | 0 | bar: Week 2 6 to Week 2 7
As a user, I want to keep track my hand gesture | 75 | 75 | 0 | Setup Ubuntu 14.04.2 LTS Operating System for laptops | 5 | All Team | Done | Week 1 1: 5
|  |  |  | Setup Ubuntu Debian Operating System for raspberry | 5 | All Team | Done | Week 1 2: 5
|  |  |  | Setup necessary software for laptop | 5 | All Team | Done | Week 1 3: 5
|  |  |  | Setup necessary software for raspberry | 5 | All Team | Done | Week 1 4: 5
|  |  |  | Writing document introduce about project | 5 | All Team | Done | Week 1 5: 5
|  |  |  | Capture images from camera | 5 | TanND + BinhLP | Done | Week 2 6: 5
|  |  |  | Save image to directory | 5 | TanND + BinhLP | Done | Week 2 7: 5
|  |  |  | Showing image to user | 5 | TanND + BinhLP | Done | Week 2 8: 5
|  |  |  | Writing document about Software Project Management Plan | 10 | All Team | Done | Week 2 9: 5; Week 2 10: 5
|  |  |  | Convert BGR background sample image to LAB sample image | 5 | LongNHK | Done | Week 2 6: 5
|  |  |  | Define color range of LAB sample color | 5 | LongNHK | Done | Week 2 7: 5
|  |  |  | Create a binary image with black background | 5 | LongNHK | Done | Week 2 8: 5
|  |  |  | Remove the color pixels is between color range: | 5 | LongNHK | Done | Week 3 11: 5
|  |  |  | Remove noises and smooth the contou | 5 | LongNHK | Done | Week 3 12: 5
|  |  |  | Find the hand in binary image | 10 | LongNHK | Done | Week 3 13: 5; Week 3 14: 5
|  |  |  | Testing function extracting color, subtracting color | 5 | LongNHK | Done | Week 3 15: 5
|  |  |  | Finding the contours on the binary image | 5 | TanND | Done | Week 3 11: 5
|  |  |  | Draws contours outlines | 5 | TanND | Done | Week 3 12: 5
|  |  |  | Testing function | 5 | TanND | Done | Week 3 13: 5
As a user, I want the system is a portable system | 75 | 75 | 0 | Learning about the power supply for devices | 5 | YNX | Done | Week 2 6: 5
|  |  |  | Learning about the types of batteries | 2 | YNX | Done | Week 2 7: 2
|  |  |  | Try different types of batteries | 3 | YNX | Done | Week 2 7: 3
|  |  |  | Learning about the voltage regulator circuit | 5 | YNX | Done | Week 2 8: 3
|  |  |  | Finding suitable type voltage regulator | 5 | BinhLP + YNX | Done | Week 2 9: 5
|  |  |  | Check the voltage regulator | 5 | BinhLP + YNX | Done | Week 2 10: 5
|  |  |  | Do testing circuit components | 5 | BinhLP + YNX | Done | Week 3 11: 5
|  |  |  | Devices running on the test circuit to test stability. | 5 | BinhLP + YNX | Done | Week 3 12: 5
|  |  |  | Welding the components together. | 5 | TanND + YNX | Done | Week 3 14: 5
|  |  |  | Testing system after welding the components together. | 5 | TanND + BinhLP | Done | Week 3 14: 5
Note on A1: Tutorial: Before the sprint, update the total working hours ("daily burnout") per day in row 31 columns I-V. For example, give 0 for sundays (if no one's working) 1- Define the tasks for each of user story (column E) 2 - Estimate the total time for each task (column F). You should UPDATE this estimations as necessary at any time. 3 - Pick up a task and change column G to your name. 4 - every sprint day (columns I-V), report how many hours you SPENT on that task on that day and update the estimated time to complete (step 2). 5 - Monitor team progress using the Sprint burndown chart below OBS: All 'modifiable' fields are in dark green color.
Note on F1: The estimated time can be updated whenever necessary (e.g. "how many more hours do I need to complete this taks?"). Changes will be reflected in the burndown chart. Once a task is completed, the time spent (yellow boxes) MUST match the estimated, i.e., the estimation will corresponding to the total of hours spent on that task.
Note on B4: formula =SUM(F3:F17)
Note on C4: formula =IF(B3<SUM(I3:I17, J3:J17, K3:K17,L3:L17,M3:M17,N3:N17,O3:O17,P3:P17,Q3:Q17,R3:R17,S3:S17,T3:T17,U3:U17,V3:V17),SUM(I3:I17, J3:J17, K3:K17,L3:L17,M3:M17,N3:N17,O3:O17,P3:P17,Q3:Q17,R3:R17,S3:S17,T3:T17,U3:U17,V3:V17),B3)
Note on D4: formula: =IF(C3>B3,$C3-(SUM(I3:I17, J3:J17, K3:K17,L3:L17,M3:M17,N3:N17,O3:O17,P3:P17,Q3:Q17,R3:R17,S3:S17,T3:T17,U3:U17,V3:V17)),$B3-(SUM(I3:I17, J3:J17, K3:K17,L3:L17,M3:M17,N3:N17,O3:O17,P3:P17,Q3:Q17,R3:R17,S3:S17,T3:T17,U3:U17,V3:V17)))

## Sprint 2 Backlog
User Story | Time (est) | Time (spent) | Time (left) | Task | Time (est) | Who's working | Status | Work Done per day per task [Hours]
[8 empty] | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6
Project Name: "Vietnamese Language Sign Recognition" Started: 12-05-2015 | [7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
| 0 | 0 | 0 | bar: Week 5 6 to Week 5 7
As a user, I want the system recognize the hand signs | 65 | 65 | 65 | Capture hand sign to create database | 5 | All Team | Done | Week 4 1: 5
|  |  |  | Writing document about Software Requirement Specification | 15 | All Team | Done | Week 4 2: 5; Week 4 3: 5; Week 4 4: 5
|  |  |  | Setup SQLite on laptop, raspberry | 2 | TanND | Done | Week 4 5: 2
|  |  |  | Design database | 4 | TanND | Done | Week 4 5: 3; Week 5 6: 1
|  |  |  | Input data for database | 4 | TanND | Done | Week 5 6: 4
|  |  |  | Convert the BGR image containing the hand to binary image containing features | 5 | LongNHK | Done | Week 4 5: 5
|  |  |  | Produce the binary image containing the hand palm from the binary image containing contour | 5 | LongNHK | Done | Week 5 6: 5
|  |  |  | Produce the binary image containing the finger lines from the binary image containing contour | 5 | LongNHK | Done | Week 5 7: 5
|  |  |  | Defining features to recognize | 5 | LongNHK | Done | Week 5 8: 5
|  |  |  | Calculate the features from these binary images | 5 | LongNHK | Done | Week 5 9: 5
|  |  |  | Training SVM | 5 | LongNHK | Done | Week 5 10: 5
|  |  |  | Recognizing the hand sign by SVM | 10 | LongNHK | Done | Week 6 11: 5; Week 6 12: 5
|  |  |  | Testing function recognize | 5 | LongNHK | Done | Week 6 13: 5
|  |  |  | Update database | 5 | TanND + YNX | Done | Week 5 6: 5
|  |  |  | Defining the meaning word of the SVM result from database | 5 | TanND + YNX | Done | Week 5 7: 5
|  |  |  | Designing QT Linux GU | 3 | BinhLP + YNX | Done | Week 4 5: 3
|  |  |  | Testing design when display in LCD | 2 | BinhLP + YNX | Done | Week 4 5: 2
As a user, I want to receive the recognition result via text and sound | 50 | 50 | 0 | Learn some text to speech opensource | 5 | BinhLP | Done | Week 5 6: 5
|  |  |  | Testing and compare some text to speech opensource | 5 | BinhLP | Done | Week 5 7: 5
|  |  |  | Setup espeak software for laptop, raspberry | 5 | BinhLP + YNX | Done | Week 5 10: 5
|  |  |  | Changing pronunciation of alphabet | 10 | TanND + BinhLP | Done | Week 5 8: 5; Week 5 9: 5
|  |  |  | Showing the recognition result of each alphabet | 10 | YNX | Done | Week 5 8: 5; Week 5 9: 5
|  |  |  | Join recognition result become syllable and a complete word | 5 | TanND + YNX | Done | Week 6 11: 5
|  |  |  | Showing the recognition result via sound | 10 | TanND + BinhLP | Done | Week 6 12: 5; Week 6 13: 5
|  |  |  | Testing, changing pronunciation of syllable | 10 | YNX | Done | Week 6 12: 5; Week 6 13: 5
Note on A1: Tutorial: Before the sprint, update the total working hours ("daily burnout") per day in row 31 columns I-V. For example, give 0 for sundays (if no one's working) 1- Define the tasks for each of user story (column E) 2 - Estimate the total time for each task (column F). You should UPDATE this estimations as necessary at any time. 3 - Pick up a task and change column G to your name. 4 - every sprint day (columns I-V), report how many hours you SPENT on that task on that day and update the estimated time to complete (step 2). 5 - Monitor team progress using the Sprint burndown chart below OBS: All 'modifiable' fields are in dark green color.
Note on F1: The estimated time can be updated whenever necessary (e.g. "how many more hours do I need to complete this taks?"). Changes will be reflected in the burndown chart. Once a task is completed, the time spent (yellow boxes) MUST match the estimated, i.e., the estimation will corresponding to the total of hours spent on that task.
Note on B4: formula =SUM(F3:F17)
Note on C4: formula =IF(B3<SUM(I3:I17, J3:J17, K3:K17,L3:L17,M3:M17,N3:N17,O3:O17,P3:P17,Q3:Q17,R3:R17,S3:S17,T3:T17,U3:U17,V3:V17),SUM(I3:I17, J3:J17, K3:K17,L3:L17,M3:M17,N3:N17,O3:O17,P3:P17,Q3:Q17,R3:R17,S3:S17,T3:T17,U3:U17,V3:V17),B3)
Note on D4: formula: =IF(C3>B3,$C3-(SUM(I3:I17, J3:J17, K3:K17,L3:L17,M3:M17,N3:N17,O3:O17,P3:P17,Q3:Q17,R3:R17,S3:S17,T3:T17,U3:U17,V3:V17)),$B3-(SUM(I3:I17, J3:J17, K3:K17,L3:L17,M3:M17,N3:N17,O3:O17,P3:P17,Q3:Q17,R3:R17,S3:S17,T3:T17,U3:U17,V3:V17)))

## Sprint 3 Backlog
User Story | Time (est) | Time (spent) | Time (left) | Task | Time (est) | Who's working | Status | Work Done per day per task [Hours]
[8 empty] | Week 6 |  | Week 7 |  |  |  |  | Week 8 |  |  |  |  | Week 9
Project Name: "Vietnamese Language Sign Recognition" Started: 12-05-2015 | [7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| 0 | 0 | 0 | bar: Week 7 6 to Week 7 7
As a user, I want to control the system functions by hand gesture | 75 | 75 | 0 | Writing Design Description document | 20 | All Team | Done | Week 6 1: 5; Week 6 2: 5; Week 7 3: 5; Week 7 4: 5
|  |  |  | Defining operations of function | 10 | LongNHK + TanND | Done | Week 7 5: 5; Week 7 6: 5
|  |  |  | Defining hand sign to control the system | 5 | LongNHK + TanND | Done | Week 7 7: 5
|  |  |  | Recognizing the control hand sign | 10 | LongNHK + TanND | Done | Week 8 8: 5; Week 8 9: 5
|  |  |  | Implementing operations of function | 10 | LongNHK + TanND | Done | Week 8 10: 5; Week 8 11: 5
|  |  |  | Designing QT Linux GUI | 5 | LongNHK + TanND | Done | Week 8 12: 5
|  |  |  | Testing GUI on LCD , change GUI | 5 | TanND | Done | Week 9 15: 5
|  |  |  | Synchronize between hand gestures and operations of function | 10 | LongNHK + TanND | Done | Week 9 13: 5; Week 9 14: 5
|  |  |  | Testing control the system function by hand gesture | 5 | LongNHK | Done | Week 9 15: 5
As a user, I want to know remaining of battery capacity | 75 | 75 | 0 | Learning about the types of chip voltage comparator | 5 | BinhLP + YNX | Done | Week 7 5: 5
|  |  |  | Choosing chip voltage comparator | 5 | BinhLP + YNX | Done | Week 7 6: 5
|  |  |  | Learning about the types of zener | 5 | BinhLP + YNX | Done | Week 7 7: 5
|  |  |  | Circuit design | 5 | BinhLP + YNX | Done | Week 8 8: 5
|  |  |  | Circuit tested by software proteus | 5 | BinhLP + YNX | Done | Week 8 9: 5
|  |  |  | Constructing circuit | 10 | BinhLP + YNX | Done | Week 8 10: 5; Week 8 11: 5
|  |  |  | Testing circuit with battery | 5 | BinhLP + YNX | Done | Week 8 12: 5
|  |  |  | Adjusting the device components | 5 | BinhLP + YNX | Done | Week 9 13: 5
|  |  |  | Connecting to the system | 5 | BinhLP + YNX | Done | Week 9 14: 5
|  |  |  | Run system to check stability with this circuit. | 5 | BinhLP + YNX | Done | Week 9 15: 5
Note on A1: Tutorial: Before the sprint, update the total working hours ("daily burnout") per day in row 31 columns I-V. For example, give 0 for sundays (if no one's working) 1- Define the tasks for each of user story (column E) 2 - Estimate the total time for each task (column F). You should UPDATE this estimations as necessary at any time. 3 - Pick up a task and change column G to your name. 4 - every sprint day (columns I-V), report how many hours you SPENT on that task on that day and update the estimated time to complete (step 2). 5 - Monitor team progress using the Sprint burndown chart below OBS: All 'modifiable' fields are in dark green color.
Note on F1: The estimated time can be updated whenever necessary (e.g. "how many more hours do I need to complete this taks?"). Changes will be reflected in the burndown chart. Once a task is completed, the time spent (yellow boxes) MUST match the estimated, i.e., the estimation will corresponding to the total of hours spent on that task.
Note on B4: formula =SUM(F3:F17)
Note on C4: formula =IF(B3<SUM(I3:I17, J3:J17, K3:K17,L3:L17,M3:M17,N3:N17,O3:O17,P3:P17,Q3:Q17,R3:R17,S3:S17,T3:T17,U3:U17,V3:V17),SUM(I3:I17, J3:J17, K3:K17,L3:L17,M3:M17,N3:N17,O3:O17,P3:P17,Q3:Q17,R3:R17,S3:S17,T3:T17,U3:U17,V3:V17),B3)
Note on D4: formula: =IF(C3>B3,$C3-(SUM(I3:I17, J3:J17, K3:K17,L3:L17,M3:M17,N3:N17,O3:O17,P3:P17,Q3:Q17,R3:R17,S3:S17,T3:T17,U3:U17,V3:V17)),$B3-(SUM(I3:I17, J3:J17, K3:K17,L3:L17,M3:M17,N3:N17,O3:O17,P3:P17,Q3:Q17,R3:R17,S3:S17,T3:T17,U3:U17,V3:V17)))

## Sprint 4 Backlog
User Story | Time (est) | Time (spent) | Time (left) | Task | Time (est) | Who's working | Status | Work Done per day per task [Hours]
[8 empty] | Week 9 |  | Week 10 |  |  |  |  | Week 11 |  |  |  |  | Week 12
Project Name: "Vietnamese Language Sign Recognition" Started: 12-05-2015 | [7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
| 0 | 0 | 0 | bar: Week 10 6 to Week 10 7
As a user, I want to increase the accuracy of the recognition result | 45 | 45 | 45 | Defining more features to recognize | 10 | LongNHK + TanND | Done | Week 9 1: 5; Week 9 2: 5
|  |  |  | Extracting features | 10 | LongNHK + TanND | Done | Week 10 3: 5; Week 10 4: 5
|  |  |  | Training SVM | 5 | LongNHK + TanND | Done | Week 10 5: 5
|  |  |  | Providing two LEDs to balance light | 10 | BinhLP + YNX | Done | Week 9 1: 5; Week 9 2: 5
|  |  |  | Providing background | 5 | BinhLP + YNX | Done | Week 10 3: 5
|  |  |  | Improving camera setting | 10 | BinhLP + YNX | Done | Week 10 4: 5; Week 10 5: 5
|  |  |  | Improving background - hand color subtraction | 5 | LongNHK + TanND | Done | Week 10 6: 5
|  |  |  | Capturing new database | 5 | All Team | Done | Week 10 7: 5
|  |  |  | Testing recognition hand sign | 5 | BinhLP + YNX | Done | Week 11 8: 5
|  |  |  | Writing document System Implementation & Test | 15 | All Team | Done | Week 12 15: 5; Week 12 16: 5; Week 12 17: 5
As a user, I want to learn hand sign language | 40 | 40 | 0 | Defining operations of function | 10 | LongNHK + TanND | Done | Week 11 8: 5; Week 11 9: 5
|  |  |  | Creating database | 5 | LongNHK + TanND | Done | Week 11 10: 5
|  |  |  | Managing database | 10 | TanND | Done | Week 11 11: 5; Week 11 12: 5
|  |  |  | Implementing the practice function of learning | 15 | LongNHK | Done | Week 11 11: 5; Week 11 12: 5; Week 12 13: 5
|  |  |  | Testing function learn hand sign | 5 | LongNHK + BinhLP | Done | Week 12 14: 5
|  |  |  | Designing GUI | 5 | TanND + YNX | Done | Week 12 13: 5
|  |  |  | Testing GUI in LCD | 5 | TanND | Done | Week 12 14: 5
As a user, I want to turn on/off the system | 35 | 35 | 0 | Learning about the types of switch button | 5 | BinhLP + YNX | Done | Week 10 6: 5
|  |  |  | Choosing switch button | 5 | BinhLP + YNX | Done | Week 10 7: 5
|  |  |  | Testing system with switch button | 5 | BinhLP + YNX | Done | Week 11 8: 5
|  |  |  | Constructing circuit with switch button | 10 | BinhLP + YNX | Done | Week 11 9: 5; Week 11 10: 5
|  |  |  | Run system to check stability with switch button. | 5 | BinhLP + YNX | Done | Week 11 11: 5
|  |  |  | Adjusting the device components | 5 | BinhLP + YNX | Done | Week 11 12: 5
Note on A1: Tutorial: Before the sprint, update the total working hours ("daily burnout") per day in row 31 columns I-V. For example, give 0 for sundays (if no one's working) 1- Define the tasks for each of user story (column E) 2 - Estimate the total time for each task (column F). You should UPDATE this estimations as necessary at any time. 3 - Pick up a task and change column G to your name. 4 - every sprint day (columns I-V), report how many hours you SPENT on that task on that day and update the estimated time to complete (step 2). 5 - Monitor team progress using the Sprint burndown chart below OBS: All 'modifiable' fields are in dark green color.
Note on F1: The estimated time can be updated whenever necessary (e.g. "how many more hours do I need to complete this taks?"). Changes will be reflected in the burndown chart. Once a task is completed, the time spent (yellow boxes) MUST match the estimated, i.e., the estimation will corresponding to the total of hours spent on that task.
Note on B4: formula =SUM(F3:F17)
Note on C4: formula =IF(B3<SUM(I3:I17, J3:J17, K3:K17,L3:L17,M3:M17,N3:N17,O3:O17,P3:P17,Q3:Q17,R3:R17,S3:S17,T3:T17,U3:U17,V3:V17),SUM(I3:I17, J3:J17, K3:K17,L3:L17,M3:M17,N3:N17,O3:O17,P3:P17,Q3:Q17,R3:R17,S3:S17,T3:T17,U3:U17,V3:V17),B3)
Note on D4: formula: =IF(C3>B3,$C3-(SUM(I3:I17, J3:J17, K3:K17,L3:L17,M3:M17,N3:N17,O3:O17,P3:P17,Q3:Q17,R3:R17,S3:S17,T3:T17,U3:U17,V3:V17)),$B3-(SUM(I3:I17, J3:J17, K3:K17,L3:L17,M3:M17,N3:N17,O3:O17,P3:P17,Q3:Q17,R3:R17,S3:S17,T3:T17,U3:U17,V3:V17)))

## Sprint 5 Backlog
User Story | Time (est) | Time (spent) | Time (left) | Task | Time (est) | Who's working | Status | Work Done per day per task [Hours]
[8 empty] | Week 13 |  |  |  |  | Week 14
Project Name: "Vietnamese Language Sign Recognition" Started: 12-05-2015 | [7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
| 0 | 0 | 0 | bar: Week 14 6 to Week 14 7
As a user, I want to the system is boxed firm, compact | 20 | 20 | 0 | Measuring, designing the box for system | 5 | LongNHK + YNX | Done | Week 13 1: 5
|  |  |  | Compare, choose materials for box | 5 | TanND + BinhLP | Done | Week 13 1: 5
|  |  |  | Constructing box for system | 10 | All Team | Done | Week 13 2: 5; Week 13 3: 5
|  |  |  | Assembling of component | 5 | All Team | Done | Week 13 4: 5
As a user, I want the system reliable operation | 15 | 15 | 15 | Perform system testing | 10 | All Team | Done | Week 14 8: 5; Week 14 9: 5
|  |  |  | Fix some recognition bug | 5 | LongNHK + YNX | Done | Week 14 10: 5
|  |  |  | Fix pronunciation of some word | 5 | TanND + BinhLP | Done | Week 14 10: 5
As a user, I want to know how to install and use the system | 15 | 15 | 15 | Writing install guide | 3 | All Team | Done | Week 13 5: 3
|  |  |  | Writing recognize hand sign manual | 3 | All Team | Done | Week 13 5: 2; Week 14 6: 1
|  |  |  | Writing learn hand sign manual | 3 | All Team | Done | Week 14 6: 3
|  |  |  | Writing some solutions when system has problems | 3 | All Team | Done | Week 14 6: 1; Week 14 7: 2
|  |  |  | Writing complete user manual document | 3 | All Team | Done | Week 14 7: 3
Note on A1: Tutorial: Before the sprint, update the total working hours ("daily burnout") per day in row 31 columns I-V. For example, give 0 for sundays (if no one's working) 1- Define the tasks for each of user story (column E) 2 - Estimate the total time for each task (column F). You should UPDATE this estimations as necessary at any time. 3 - Pick up a task and change column G to your name. 4 - every sprint day (columns I-V), report how many hours you SPENT on that task on that day and update the estimated time to complete (step 2). 5 - Monitor team progress using the Sprint burndown chart below OBS: All 'modifiable' fields are in dark green color.
Note on F1: The estimated time can be updated whenever necessary (e.g. "how many more hours do I need to complete this taks?"). Changes will be reflected in the burndown chart. Once a task is completed, the time spent (yellow boxes) MUST match the estimated, i.e., the estimation will corresponding to the total of hours spent on that task.
Note on B4: formula =SUM(F3:F17)
Note on C4: formula =IF(B3<SUM(I3:I17, J3:J17, K3:K17,L3:L17,M3:M17,N3:N17,O3:O17,P3:P17,Q3:Q17,R3:R17,S3:S17,T3:T17,U3:U17,V3:V17),SUM(I3:I17, J3:J17, K3:K17,L3:L17,M3:M17,N3:N17,O3:O17,P3:P17,Q3:Q17,R3:R17,S3:S17,T3:T17,U3:U17,V3:V17),B3)
Note on D4: formula: =IF(C3>B3,$C3-(SUM(I3:I17, J3:J17, K3:K17,L3:L17,M3:M17,N3:N17,O3:O17,P3:P17,Q3:Q17,R3:R17,S3:S17,T3:T17,U3:U17,V3:V17)),$B3-(SUM(I3:I17, J3:J17, K3:K17,L3:L17,M3:M17,N3:N17,O3:O17,P3:P17,Q3:Q17,R3:R17,S3:S17,T3:T17,U3:U17,V3:V17)))

## User types
User
Moderator
Client administrator
Developer

## Team members
All Team
BinhLP + YNX
LongNHK + TanND
LongNHK + BinhLP
LongNHK + YNX
TanND + BinhLP
TanND + YNX

## Task statuses
TODO
Working
Done
Blocked
Verify